Project Handoff Evaluation Rubric

Complete 32-Criterion Assessment Framework

Version: 2024.1

Generated: July 02, 2025

# Executive Summary

This document outlines the comprehensive Project Handoff Evaluation Rubric used to assess 
the quality and completeness of project handoff documentation and meetings. The rubric 
consists of 32 individual criteria organized across 7 major categories, 
with a total possible score of 180 points.

The evaluation framework is designed to ensure that all critical aspects of project 
handoffs are properly documented and communicated, promoting successful project 
transitions and reducing risks.

## Key Features

• 32 comprehensive evaluation criteria

• Detailed scoring guidelines for each criterion

• Weighted scoring system (75% content + 25% foreman attendance)

• Category-based organization for systematic assessment

• Evidence-based evaluation approach

• Performance level classifications

• Industry best practice alignment

# Scoring Methodology

## Overall Scoring Approach

The rubric uses a weighted scoring system that combines content quality assessment 
with foreman attendance verification:

• Content Quality (75% weight): Evaluation against 32 criteria totaling 180 points
• Foreman Attendance (25% weight): Binary assessment worth 25 points

Final Score = (Content Score/180 × 100 × 0.75) + (Attendance Score × 0.25)

## Performance Level Classifications

| Performance Level | Score Range | Description |
| --- | --- | --- |
| EXCELLENT | 90-100% | Comprehensive coverage of all criteria |
| GOOD | 80-89% | Strong performance with minor gaps |
| SATISFACTORY | 70-79% | Adequate coverage meeting basic requirements |
| NEEDS IMPROVEMENT | 60-69% | Significant gaps requiring attention |
| UNSATISFACTORY | <60% | Major deficiencies requiring immediate action |

# Detailed Rubric Breakdown

Customer Category (6 points)

### Criterion 1: Customer Background Details

Description: Who is the customer? Prior relationship? Any specific concerns from past?

Maximum Points: 6

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Customer Identity | 2 | 2=Customer clearly named ¦ 1=Vague ¦ 0=Not identified |
| Relationship History | 2 | 2=Specific past work ¦ 1=General mention ¦ 0=No info |
| Concerns | 1 | 1=Specific concerns noted ¦ 0=No concerns |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

Timeline Category (12 points)

### Criterion 2: Project Timeline Analysis

Description: Start/end dates? Anticipated delays? Flexibility for unexpected changes?

Maximum Points: 6

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Start Info | 1 | 1=Clear start date ¦ 0=Missing/vague |
| Completion Info | 1 | 1=Clear completion date ¦ 0=Missing/vague |
| Duration/Resources | 3 | 3=All details ¦ 2=Two elements ¦ 1=One element ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 3: Project Milestones

Description: Key dates/events identified and communicated?

Maximum Points: 6

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Milestones | 2 | 2=All with dates ¦ 1=Some ¦ 0=None |
| Integration | 2 | 2=Schedule integrated ¦ 1=Basic ¦ 0=None |
| Communication | 1 | 1=Tracking plan ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

Material Category (10 points)

### Criterion 4: Material Sourcing & Availability

Description: Key materials required? Lead times? Potential impact of delay?

Maximum Points: 5

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Material Assessment | 2 | 2=Comprehensive analysis ¦ 1=Basic ID ¦ 0=Not identified |
| Lead Times | 1 | 1=Clear lead times ¦ 0=No info |
| Mitigation | 1 | 1=Actions mentioned ¦ 0=No strategies |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 5: Procurement Updates

Description: Are current procurement statuses shared and tracked?

Maximum Points: 5

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Status | 2 | 2=Detailed status/timelines ¦ 1=General ¦ 0=None |
| Updates | 1 | 1=Regular process ¦ 0=None |
| Risks | 1 | 1=Risks identified ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

Safety Category (36 points)

### Criterion 6: Site Conditions

Description: Any access issues, weather challenges, or hazards noted?

Maximum Points: 6

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Risk ID | 2 | 2=Multiple risks ¦ 1=One risk ¦ 0=No risks |
| Assessment | 1 | 1=Risk level described ¦ 0=No assessment |
| Mitigation | 2 | 2=Specific actions ¦ 1=General ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 7: Safety Considerations

Description: Are safety protocols, risks, and responsibilities discussed?

Maximum Points: 6

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Risk ID | 2 | 2=Multiple safety risks ¦ 1=One risk ¦ 0=No risks |
| Communication | 1 | 1=Protocols communicated ¦ 0=No plan |
| Mitigation | 2 | 2=Specific measures ¦ 1=General ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 8: Risk Management

Description: Are project risks identified and mitigations in place?

Maximum Points: 6

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Risk ID | 2 | 2=Multiple risks ¦ 1=One risk ¦ 0=None |
| Assessment | 1 | 1=Impact assessed ¦ 0=None |
| Mitigation | 2 | 2=Specific strategies ¦ 1=General ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 9: Work Area Protection

Description: Are barricades, signage, temporary walls planned?

Maximum Points: 6

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Protection | 2 | 2=Comprehensive plan ¦ 1=Basic ¦ 0=None |
| Signage | 2 | 2=Detailed plan ¦ 1=General ¦ 0=None |
| Timeline | 1 | 1=Implementation schedule ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 10: Access & Egress Plans

Description: How do workers/materials get in/out safely and efficiently?

Maximum Points: 6

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Routes | 2 | 2=Specific safe routes ¦ 1=General ¦ 0=None |
| Material Handling | 2 | 2=Detailed plan ¦ 1=Basic ¦ 0=None |
| Safety | 1 | 1=Safety measures ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 11: Glazing-Specific Risks

Description: Are unique risks (e.g., lifting glass, storage) considered?

Maximum Points: 6

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Risk ID | 2 | 2=Multiple glazing risks ¦ 1=Some ¦ 0=None |
| Protocols | 2 | 2=Detailed protocols ¦ 1=Basic ¦ 0=None |
| Equipment | 1 | 1=Specialized needs ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

Scope Category (6 points)

### Criterion 12: Scope of Work

Description: What's included/excluded? Are all trades and tasks covered?

Maximum Points: 6

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Scope Confirmation | 2 | 2=Detailed scope ¦ 1=Basic outline ¦ 0=Unclear |
| Coverage | 1 | 1=All trades ID ¦ 0=Incomplete |
| Issues | 2 | 2=Comprehensive ¦ 1=Basic ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

Equipment Category (6 points)

### Criterion 13: Equipment Needs

Description: Special tools/lifts/scaffolding required? Who provides what?

Maximum Points: 6

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Equipment ID | 1 | 1=Specific types listed ¦ 0=Not clear |
| Costs | 2 | 2=Specific costs ¦ 1=General ¦ 0=None |
| Provider/Coord | 2 | 2=Clear provider/timing ¦ 1=Partial ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

General Category (104 points)

### Criterion 14: Permits & Inspections

Description: Which permits are required? Status of inspections?

Maximum Points: 5

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Permits | 2 | 2=All permits with status ¦ 1=Incomplete ¦ 0=Unclear |
| Schedule | 1 | 1=Timeline provided ¦ 0=No info |
| Actions | 1 | 1=Actions described ¦ 0=No plan |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 15: Subcontractor Coordination

Description: Are subcontractors identified and scheduled?

Maximum Points: 6

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Sub ID | 2 | 2=All subs by name ¦ 1=Some ¦ 0=Unclear |
| Schedule | 2 | 2=Detailed plan ¦ 1=Basic ¦ 0=None |
| Communication | 1 | 1=Method defined ¦ 0=No plan |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 16: Communication Plan

Description: Who's the main contact? Method/frequency of updates?

Maximum Points: 6

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Contacts | 2 | 2=Clear contacts with roles ¦ 1=Some ¦ 0=Unclear |
| Methods | 2 | 2=Specific methods/frequency ¦ 1=General ¦ 0=None |
| Schedule | 1 | 1=Update schedule ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 17: Drawing/Spec Review

Description: Have relevant drawings/specs been reviewed and explained?

Maximum Points: 5

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Review | 2 | 2=All documents reviewed ¦ 1=Some ¦ 0=None |
| Understanding | 1 | 1=Confirmed with team ¦ 0=No confirmation |
| Actions | 1 | 1=Actions identified ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 18: Change Order Procedure

Description: Is the change process understood? Forms, approvals, pricing?

Maximum Points: 6

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Process | 2 | 2=Complete process ¦ 1=Basic ¦ 0=None |
| Approvals | 2 | 2=Clear hierarchy ¦ 1=Some info ¦ 0=Unclear |
| Pricing | 1 | 1=Method explained ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 19: Budget/Cost Tracking

Description: Is the budget reviewed and roles defined for tracking costs? Do we have an NTE?

Maximum Points: 6

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Budget | 2 | 2=Specific amounts/NTE ¦ 1=General ¦ 0=None |
| Roles | 2 | 2=Clear responsibilities ¦ 1=Some ¦ 0=Unclear |
| Process | 1 | 1=Monitoring defined ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 20: Quality Control Measures

Description: Inspections, punch list process, workmanship standards?

Maximum Points: 6

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Inspections | 2 | 2=Detailed schedule ¦ 1=Basic ¦ 0=None |
| Standards | 2 | 2=Specific standards ¦ 1=General ¦ 0=None |
| Punch List | 1 | 1=Clear process ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 21: Emergency Contacts

Description: Who to call for major issues? Is this list documented/shared?

Maximum Points: 5

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Contacts | 2 | 2=Complete list ¦ 1=Some ¦ 0=None |
| Documentation | 1 | 1=Documented/accessible ¦ 0=None |
| Protocol | 1 | 1=Communication plan ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 22: Storage/Logistics

Description: Where are materials stored? Delivery coordination?

Maximum Points: 5

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Storage | 2 | 2=Specific locations/security ¦ 1=General ¦ 0=None |
| Delivery | 1 | 1=Schedule/coordination ¦ 0=None |
| Access | 1 | 1=Access procedures ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 23: Insurance & Bonding

Description: Confirm coverage and any specific policy limitations?

Maximum Points: 5

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Coverage | 2 | 2=All requirements confirmed ¦ 1=Basic ¦ 0=None |
| Limitations | 1 | 1=Limitations noted ¦ 0=None |
| Compliance | 1 | 1=Actions for compliance ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 24: Legal/Contract Requirements

Description: Are contract obligations highlighted and risks reviewed?

Maximum Points: 6

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Obligations | 2 | 2=Specific obligations ¦ 1=General ¦ 0=None |
| Risks | 2 | 2=Analyzed with mitigation ¦ 1=Basic ¦ 0=None |
| Compliance | 1 | 1=Compliance plan ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 25: Neighbor/Adjacent Property Coordination

Description: Have neighbors been notified? Special coordination needed?

Maximum Points: 5

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Notification | 2 | 2=Properly notified ¦ 1=Some ¦ 0=None |
| Coordination | 1 | 1=Requirements identified ¦ 0=None |
| Communication | 1 | 1=Ongoing plan ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 26: Roofing-Specific Hazards

Description: Are fall protection, staging, and weather exposure addressed?

Maximum Points: 6

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Fall Protection | 2 | 2=Comprehensive plan ¦ 1=Basic ¦ 0=None |
| Staging | 2 | 2=Detailed plan ¦ 1=Basic ¦ 0=None |
| Weather | 1 | 1=Risks addressed ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 27: Debrief with Outgoing Team

Description: Has the outgoing crew/team been debriefed for issues or lessons learned?

Maximum Points: 6

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Debrief | 2 | 2=Comprehensive with docs ¦ 1=Basic ¦ 0=None |
| Issues | 2 | 2=Specific issues documented ¦ 1=Some ¦ 0=None |
| Transfer | 1 | 1=Knowledge transferred ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 28: Client Communication Plan

Description: How and when is the client updated?

Maximum Points: 6

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Schedule | 2 | 2=Specific schedule ¦ 1=General ¦ 0=None |
| Contacts | 2 | 2=Primary/backup contacts ¦ 1=Some ¦ 0=None |
| Content | 1 | 1=Content defined ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 29: Escalation Pathway

Description: When and how are issues escalated?

Maximum Points: 5

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Triggers | 2 | 2=Clear triggers ¦ 1=Some ¦ 0=None |
| Process | 1 | 1=Step-by-step ¦ 0=None |
| Contacts | 1 | 1=Contact chain ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 30: Temporary Systems

Description: Are any temp power, HVAC, drainage setups explained?

Maximum Points: 5

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Requirements | 2 | 2=All systems with specs ¦ 1=Some ¦ 0=None |
| Installation | 1 | 1=Timeline/responsibility ¦ 0=None |
| Coordination | 1 | 1=Trade coordination ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 31: Conflict Resolution Strategy

Description: Are conflicts resolved via defined process or chain of command?

Maximum Points: 5

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Process | 2 | 2=Clear process/steps ¦ 1=Basic ¦ 0=None |
| Authority | 1 | 1=Chain of command ¦ 0=None |
| Documentation | 1 | 1=Tracking process ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

### Criterion 32: Post-Handoff Follow-Up

Description: Is there a scheduled check-in after handoff?

Maximum Points: 5

#### Scoring Breakdown:

| Component | Points | Scoring Guide |
| --- | --- | --- |
| Schedule | 2 | 2=Specific meetings/agenda ¦ 1=General ¦ 0=None |
| Responsibility | 1 | 1=Clear responsibility ¦ 0=None |
| Metrics | 1 | 1=Success criteria ¦ 0=None |
| Universal Check | 1 | 1=2+ concrete details ¦ 0=Vague |

# Category Weight Analysis

| Category | Max Points | Criteria Count | Weight % |
| --- | --- | --- | --- |
| Customer | 6 | 1 | 3.3% |
| Timeline | 12 | 2 | 6.7% |
| Material | 10 | 2 | 5.6% |
| Safety | 36 | 6 | 20.0% |
| Scope | 6 | 1 | 3.3% |
| Equipment | 6 | 1 | 3.3% |
| General | 104 | 19 | 57.8% |
| TOTAL | 180 | 32 | 100.0% |

Key observations about category weighting:

• General category dominates with 57.8% of total points (104/180)
• Safety is the second-largest category with 20.0% of total points (36/180)
• Timeline and Material categories provide balanced coverage (6.7% and 5.6% respectively)
• Customer, Scope, and Equipment categories each represent 3.3% of total points
• This weighting reflects the comprehensive nature of project management requirements

The high weight of the General category reflects the extensive administrative and 
coordination requirements typical in complex construction projects.

# Usage Guidelines

## For Evaluators

1. Review the complete document or transcript before scoring
2. Score each criterion independently based on evidence found
3. Use the "Universal Check" as a quality gate for concrete details
4. Document specific evidence to support scoring decisions
5. Be consistent in applying scoring criteria across all evaluations
6. Consider the context and project complexity when evaluating

## For Project Teams

1. Use this rubric as a checklist during handoff preparation
2. Ensure all 32 criteria are addressed in handoff documentation
3. Include specific details and concrete information for each criterion
4. Verify foreman attendance and participation in handoff meetings
5. Review scoring guidelines to understand quality expectations
6. Address identified gaps before project transition

## Quality Assurance Recommendations

• Conduct regular calibration sessions among evaluators
• Maintain examples of excellent, good, and poor handoff documentation
• Track scoring trends over time to identify systemic issues
• Provide feedback to project teams based on evaluation results
• Update rubric criteria based on industry best practices and lessons learned
• Ensure foreman participation is properly documented and verified